## Summary
2105-11-14
Health | Project Title | Project Type | Project Owner | Created | Last Modified | Last Report | Number of collaborators
70 | ASU Visualization | Code | Rajat Aggarwal | 2015-11-03
70 | SSO With Certificates | Code
70 | Internet of Things | Research
| Regression analysis on gas prices | Research | Sushrut Dabir | 2015-11-10
70

## ASUVisualizations
Project Title: ASU Visualizations
Project Owner: Rajat Aggarwal
Date | 11.14.2015 | 11.21.2015 | 11.28.2015 | 12.5.2015 | 12.12.2015 | 12.19.2015 | 12.25.2015
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7
Milestones | 1. Identify problem statement of visualization. 2. Create data collection strategy | 1. Collect data. Clean and filter | 1. Perform analysis on data - needs to be throughly documented | 1. Prototype visualization | Visualization - overview design | Visualization - Details on demand | Visualization - Zoom & Filter
Report sent (Y/N)
Milestone reached (%)
Quality factor ([0-0.2])
Quality adherence (%)
Status
Notes/ Issues/ Requests for GESSA team

## SSOWithCertificates
Project Title: SSO with Certificates
Project Owner: Ankita Chandak and Nitin Karda
Date | 11.14.2015 | 11.21.2015 | 11.28.2015 | 12.5.2015 | 12.12.2015 | 12.19.2015 | 12.25.2015
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7
Milestones | Sharing sessions between apps (Research on framework laravel) | Continue research on session sharing and build a prototype, (Think about how sessions will be stored.) | Continue on prototype building and demo sharing session between apps | Work on extracting identity information from the certificate | Build a prototype using cert information and pass it to the application. | TBD | TBD
Report sent (Y/N)
Milestone reached (%)
Quality factor ([0-0.2])
Quality adherence (%)
Status
Notes/ Issues/ Requests for GESSA team

## IoT
Project Title: Internet Of Things
Project Owner: Karteek Rupakula
Date | 11.14.2015 | 11.21.2015 | 11.28.2015 | 12.5.2015 | 12.12.2015 | 12.19.2015 | 12.25.2015
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7
Milestones | 1.Research about IoT companies and projects. 2.find out about the technical aspects of IoT | 1.Create a short report on IOT communication protocols | Extend the report to describe more about protocols and hardwares (should be 15 pages long) | 1.Come up with an idea to do projects on IoT using Rasberry Pi or other platforms 2. Learn about the required programming language which is compatible with the chosen hardware | 1.Finalize on the hardware to be used and start the implementaion. 2. Have the project hosted | TBD | TBD
Report sent (Y/N)
Milestone reached (%)
Quality factor ([0-0.2])
Quality adherence (%)
Status
Notes/ Issues/ Requests for GESSA team | Looking for someone who knows Rasberry-Pi

## gessa.org
Project Title: gessa.org
Project Owner: Pramodh Natarajan
Date | 11.14.2015 | 11.21.2015 | 11.28.2015 | 12.5.2015 | 12.12.2015 | 12.19.2015 | 12.25.2015
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7
Milestones | 1. Prepare complete requirement 2. Get repository ready 3. Setup JIRA tasks | 1. Prepare the main template for entire website (Jumbotron) 2. Bootstrap knowledge sharing with collaborators | 1. Finalize template with header and footer 2. Get home page ready (Carousal, Navbar) | Create plugins for: 1. event 2. calendar | Create pages for 1. Forms 2. People 3. About Us 4. Contact Us | Thorough testing, code review and bug fixing | Deploy website onto gessa.org using GitHub pages CNAME and updating DNS provider properties
Report sent (Y/N)
Milestone reached (%)
Quality factor ([0-0.2])
Quality adherence (%)
Status
Notes/ Issues/ Requests for GESSA team

## Regression Analysis-Gas Prices
Project Title: Regression analysis on gas prices
Project Owner: Sushrut Dabir
Date | 11.14.2015 | 11.21.2015 | 11.28.2015 | 12.5.2015 | 12.12.2015 | 12.19.2015 | 12.25.2015
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7
Milestones | 1. Identify Scope and limitations of the project. 2. Determine possible factors affecting the main response variable. 3. Collect relevant data | 1. Clean data, compile. 2. Learn basic functions for regression analysis in R/SAS. 3. Run preliminary regression on the software | 1. Identify whether some factors can be eliminated 2. Check the hypothesis results for significance of individual factors and (if possible) their interactions. | N/A | N/A | 1. Remove the factors that seem insignificant. 2. Run regression with the reduced model. | 1. Interpret the final results. 2. Check for practical significance of the factors that apeared statistically significant. 3. Conclude (hypothetically) how the results can be used in real life policy making by the Government.
Report sent (Y/N)
Milestone reached (%)
Quality factor ([0-0.2])
Quality adherence (%)
Status
Notes/ Issues/ Requests for GESSA team